## Statistics
Roebling Scrum Board - Sprint 13 | [9 empty] | Ideas | Comments | Assigned | Completed | Sessions
Ideas | Text | 75 | Sol | 6 | Brian Dec | 0 | Votes Available | 80 | 2020-01-06 | 24 | 4 | 19 | 0 | 18 | Assigned | 83 | Completed | 1
| Title | 9 | Jordan | 32 | Gwen Grant | 7 | Votes Assigned | 6 | 2020-01-07 | 52 | 34 | 31 | 0 | 41 | Not Assigned | 10 | Incomplete | 92
| Photo | 0 | Joy | 8 | Jan Valenzuela | 0 |  |  | 2020-01-08 | 76 | 44 | 35 | 1 | 50
| Video | 0 | Brian | 12 | John Tarczewski | 0 |  |  | 2020-01-09 | 76 | 45 | 35 | 1 | 55
| File | 0 | Gwen | 20 | Jordan Conley | 53 |  |  | 2020-01-10 | 78 | 45 | 35 | 1 | 62
| Whiteboard | 0 | Team Member | 15 | Joy Iaconianni | 32 |  |  | 2020-01-11 | 78 | 45 | 35 | 1 | 62
| Index Card | 0 |  |  | Paul Scilingo | 1 |  |  | 2020-01-12 | 78 | 45 | 35 | 1 | 62
[5 empty] | Sol Posada | 0 |  |  | 2020-01-13 | 78 | 45 | 35 | 1 | 66
[9 empty] | 2020-01-14 | 82 | 51 | 39 | 1 | 72
[9 empty] | 2020-01-15 | 83 | 51 | 39 | 1 | 75
[9 empty] | 2020-01-16 | 85 | 52 | 48 | 1 | 80
[9 empty] | 2020-01-17 | 85 | 52 | 48 | 1 | 80
[9 empty] | 2020-01-18 | 85 | 52 | 48 | 1 | 80
[9 empty] | 2020-01-19 | 85 | 52 | 48 | 1 | 80
[9 empty] | 2020-01-20 | 85 | 52 | 48 | 1 | 80
[9 empty] | 2020-01-21 | 86 | 53 | 48 | 1 | 88
[9 empty] | 2020-01-22 | 90 | 53 | 82 | 1 | 96
[9 empty] | 2020-01-23 | 93 | 55 | 83 | 1 | 111
Tasks Assigned and Completed
Sessions

## RoeblingScrumBoardSprint13
Storm Title | Roebling Scrum Board - Sprint 13
Identifier | Idea | Thumbnail | Type | Votes | Comments | Legend | Shape | X | Y | Section | Section Type | Creator | Assigned To | Date Due | Date Completed | Date Created
d3c15d51-0b59-45da-a8c8-24f7f62b3242 | WI Update Planning |  | Text | 0 | 1 | Jordan | Square | 25 | 212 | 1. Backlog - High Prio | shape | Joy Iaconianni | Jordan Conley |  |  | 2020-Jan-08 07:07:48
aed04b18-f66f-4778-8299-3cb615aaef29 | Guidance Doc ¦ Req Map - Draft |  | Text | 0 | 1 | Jordan | Square | 321 | 210 | 1. Backlog - High Prio | shape | Joy Iaconianni | Jordan Conley |  |  | 2020-Jan-07 01:01:57
502439fa-e4d1-4667-9027-1aa53050a2ff | US Q4 Workshop ¦ RTM Transition |  | Text | 0 | 1 | Jordan | Square | 526 | 212 | 1. Backlog - High Prio | shape | Joy Iaconianni | Jordan Conley |  |  | 2020-Jan-08 07:08:00
f2dac4ab-077d-41e0-8e89-c5c0d4afd3fc | Create Common Use Survey for L3 Partners |  | Text | 0 | 1 | Gwen | Square | 781 | 212 | 1. Backlog - High Prio | shape | Joy Iaconianni | Gwen Grant |  |  | 2020-Jan-08 07:09:11
11fc6fab-04a6-4edf-bf3a-5704a71f3890 | Guidance Doc ¦ DEx - Draft and Review |  | Text | 0 | 0 | Gwen | Square | 1027 | 210 | 1. Backlog - High Prio | shape | Gwen Grant | Gwen Grant |  |  | 2020-Jan-08 07:14:16
a9a5a343-4ad0-4f53-8113-0d4cccb9abec | Implementation Execution ¦ L3 Training TBD |  | Text | 0 | 0 | Gwen | Square | 1290 | 212 | 1. Backlog - High Prio | shape | Joy Iaconianni | Gwen Grant |  |  | 2020-Jan-08 07:07:42
946b1153-7991-4443-9aed-859f23dbd4c9 | Feedback L2T ¦ Interrelationship of Tools |  | Text | 0 | 0 | Gwen | Square | 1035 | 408 | 1. Backlog - High Prio | shape | Joy Iaconianni | Gwen Grant |  |  | 2020-Jan-08 07:08:48
677cea72-4316-4d77-bb4c-a8e15b7105c1 | Finalize the L3 Project List |  | Text | 0 | 0 | Gwen | Square | 1304 | 415 | 1. Backlog - High Prio | shape | Gwen Grant | Gwen Grant |  |  | 2020-Jan-08 07:12:03
9fddb193-fb6a-417a-9528-e22d7541e11f | Implementation Execution ¦ L3 Training TFS |  | Text | 0 | 0 | Sol | Square | 25 | 424 | 1. Backlog - High Prio | shape | Joy Iaconianni | Sol Posada |  |  | 2020-Jan-08 07:07:20
27eafe9a-0549-4e0f-846a-552c3410c957 | Create L3 Training Content |  | Text | 0 | 0 | Sol | Square | 272 | 424 | 1. Backlog - High Prio | shape | Joy Iaconianni | Sol Posada |  |  | 2020-Jan-08 07:07:01
a7f079ed-36b1-4550-9d16-f09ddc069da5 | Weibull Stat Guidance |  | Text | 0 | 1 | Team Member | Square | 526 | 424 | 1. Backlog - High Prio | shape | Paul Scilingo | Paul Scilingo |  |  | 2020-Jan-23 01:12:36
86a032a7-5516-4bff-b15c-c50640d7c716 | L3 Training Dry Run w/ Ankle Fusion |  | Text | 0 | 1 | Jordan | Square | 25 | 636 | 1. Backlog - High Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-06 06:53:25
e14a2ff6-b28b-4c58-a6b0-59242f7a250e | CORe 3 of 6 ¦ Labeling (Gen1 Solution) |  | Text | 0 | 1 | Team Member | Square | 781 | 636 | 1. Backlog - High Prio | shape | Joy Iaconianni | Jan Valenzuela |  |  | 2020-Jan-08 07:09:44
a5011a53-8ff1-468c-96dd-8ec053cd9bab | Guidance Doc ¦ Writing Good Requirements |  | Text | 0 | 0 | Brian | Square | 1290 | 636 | 1. Backlog - High Prio | shape | Joy Iaconianni | Brian Dec |  |  | 2020-Jan-08 07:16:06
7abc107d-9511-4d0d-a366-ce2088b14d29 | Feedback L2T ¦ Evidence Generation |  | Text | 0 | 0 | Gwen | Square | 25 | 848 | 1. Backlog | shape | Joy Iaconianni | Gwen Grant |  |  | 2020-Jan-08 07:08:57
eaa8f6db-e75d-4a4f-9c44-fac97f1760ea | Feedback L2T ¦ Overview of Procedure Impact |  | Text | 0 | 0 | Jordan | Square | 272 | 848 | 1. Backlog - Med Prio | shape | Joy Iaconianni | Jordan Conley |  |  | 2020-Jan-08 07:08:32
1fa9922c-0b34-4d81-8512-e7f7db462eb6 | Req. Spec. ¦ Procedure Based FDR vs. Device Specific |  | Text | 0 | 1 | Brian | Square | 526 | 848 | 1. Backlog - Med Prio | shape | Joy Iaconianni | Brian Dec |  |  | 2020-Jan-08 07:15:18
79bc2bb2-942f-4bbd-a7fe-8a01516c3652 | CORe 3 of 6 ¦ Packaging (Gen1 Solution) |  | Text | 0 | 1 | Team Member | Square | 781 | 848 | 1. Backlog - Med Prio | shape | Joy Iaconianni | Jan Valenzuela |  |  | 2020-Jan-08 07:14:01
d884a657-00e3-4b7b-b59a-87ecbb74fec0 | DMD Assessment for L3 Training |  | Text | 0 | 1 | Jordan | Square | 1035 | 848 | 1. Backlog - Med Prio | shape | Joy Iaconianni | Brian Dec |  |  | 2020-Jan-07 01:02:28
dbf38b19-18e4-4d06-9ff4-52c54e2e925a | Req. Spec. ¦ Part Number to Requirement Traceability |  | Text | 0 | 1 | Brian | Square | 1290 | 848 | 1. Backlog - Med Prio | shape | Joy Iaconianni | Brian Dec |  |  | 2020-Jan-08 07:15:02
9fdd6eea-ec6d-4f34-b251-e1d7b9aff46a | CORe 3 of 6 ¦ Bio Comp (Gen1 Solution) |  | Text | 0 | 1 | Team Member | Square | 25 | 1060 | 1. Backlog | shape | Joy Iaconianni | Jan Valenzuela |  |  | 2020-Jan-08 07:14:36
2cf5501e-5d90-4e9d-82ed-71b13a04584e | Standard DEx Tool - Stakeholder Analysis - Phase 1 (M) |  | Text | 0 | 1 | Joy | Gem | 526 | 1060 | 1. Backlog - Med Prio | shape | Joy Iaconianni | Joy Iaconianni |  |  | 2020-Jan-14 01:52:30
7d4bfe1f-087f-42d2-91cb-3be39f282698 | Standard DEx Tool - Multi-Generational Plan - Phase 1 (M) |  | Text | 0 | 2 | Joy | Gem | 781 | 1060 | 1. Backlog - Med Prio | shape | Joy Iaconianni | Joy Iaconianni |  |  | 2020-Jan-14 01:52:08
b253a17d-8453-440b-ad09-922f069efe8c | RTM ¦ External Parts List |  | Text | 0 | 2 | Jordan | Square | 1035 | 1060 | 1. Backlog - Med Prio | shape | Joy Iaconianni | Jordan Conley |  |  | 2020-Jan-07 01:03:03
2297942d-ad75-440d-975b-93d12d6c4a53 | CORe 3 of 6 ¦ F&DR S5 (Gen1 Solution) |  | Text | 0 | 1 | Team Member | Square | 1290 | 1060 | 1. Backlog | shape | Joy Iaconianni | Jan Valenzuela |  |  | 2020-Jan-08 07:14:21
97a5d209-6cdb-4c8d-83d6-26f4d38f52cf | Partner 7 of n ¦Maxframe Pilot |  | Text | 0 | 1 | Brian | Square | 324 | 1067 | 1. Backlog - Med Prio | shape | Joy Iaconianni | Brian Dec |  |  | 2020-Jan-07 01:01:40
254f673d-f68c-46da-89fe-9cfc9e3cfbbb | Roll-out Communication Plan |  | Text | 0 | 0 | Gwen | Square | 435 | 1355 | 1. Backlog - Low Prio | shape | Gwen Grant | Gwen Grant |  |  | 2020-Jan-08 07:13:23
4051f1f0-798e-4311-b0d5-8ebf89b7a9ec | Marketing Claims |  | Text | 0 | 0 | Brian | Square | 1011 | 1355 | 1. Backlog - Low Prio | shape | Joy Iaconianni | Brian Dec |  |  | 2020-Jan-07 01:02:47
5fdbf7fd-0ab9-4e7e-9a84-858564bc7c8c | Guidance Doc ¦ DEx - Finalize and Publish |  | Text | 0 | 0 | Gwen | Square | 156 | 1362 | 1. Backlog - Low Prio | shape | Gwen Grant | Gwen Grant |  |  | 2020-Jan-08 07:14:40
556c3852-9ba3-474b-b03b-4f40d1b8be94 | Guidance Doc ¦ RTM |  | Text | 0 | 1 | Brian | Square | 862 | 1362 | 1. Backlog - Low Prio | shape | Joy Iaconianni | Jordan Conley |  |  | 2020-Jan-07 01:01:48
d99a3db6-f0a3-4846-a784-a61b7cfb2a4e | RTM ¦ Windchill Readiness |  | Text | 0 | 2 | Jordan | Square | 200 | 1584 | 1. Backlog - Low Prio | shape | Joy Iaconianni | Jordan Conley |  |  | 2020-Jan-07 01:02:41
a088c4c1-11be-4511-b67d-fc7197b0dafb | Complete Reqt Map so TFS Confidence Eval can begin (M) |  | Text | 0 | 0 | Jordan | Square | 748 | 1647 | 1. Backlog - Low Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-22 09:28:47
7ced1f49-3cdb-4249-8b26-c054a61ff3e5 | Support Pelvis Formative Usability Labs (S) |  | Text | 0 | 0 | Joy | Square | 1219 | 1645 | 1. Backlog - Low Prio | shape | Jordan Conley |  |  |  | 2020-Jan-22 08:57:01
1224992c-af16-4455-b77f-1006266120f8 | Prep for Feb Town Hall (M) |  | Text | 0 | 0 | Gwen | Square | 1003 | 1654 | 1. Backlog - Low Prio | shape | Jordan Conley | Gwen Grant |  |  | 2020-Jan-22 08:52:26
54534f13-fc63-4b8b-8309-2ade3e698444 | Req. Spec ¦ Draft "How to write V&V Strategy" (S) |  | Text | 0 | 1 | Brian | Square | 2461 | 830 | 2. To Do - Med Prio | shape | Jordan Conley | Brian Dec |  |  | 2020-Jan-06 06:53:24
ddfc35e8-05f7-4242-b5e4-7fa8ee7f137e | Coordinate w/ TPP workstream in Scope TTM (S) |  | Text | 0 | 1 | Gwen | Square | 2374 | 1405 | 2. To Do - Low Prio | shape | Jordan Conley | Gwen Grant |  |  | 2020-Jan-06 06:53:24
cad5771d-e7d8-4239-8b38-8b56f079c41b | Draft CA - Complete Remaining Redlines (M) |  | Text | 0 | 2 | Jordan | Square | 3279 | 275 | 3. In Work - High Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-06 06:53:25
696bb571-3022-400a-8ad0-22f8e554fb44 | Finalize & Post TFS Guidance (L) |  | Text | 0 | 1 | Sol | Square | 3560 | 275 | 3. In Work - High Prio | shape | Jordan Conley | Sol Posada |  |  | 2020-Jan-06 06:53:25
b86d5231-1d10-43ae-b83f-e792d5580344 | Guidance Doc ¦ Dex - Develop Outline (L) |  | Text | 3 | 1 | Gwen | Square | 3829 | 279 | 3. In Work - High Prio | shape | Jordan Conley | Gwen Grant |  |  | 2020-Jan-06 06:53:49
40dedc17-5060-4686-a80d-ff8aef3e2778 | Convert Roebling (676) Process outline into 012 appendix 1 (L) |  | Text | 0 | 1 | Brian | Square | 3454 | 502 | 3. In Work - High Prio | shape | Jordan Conley | Brian Dec |  |  | 2020-Jan-06 06:53:24
ca87be64-b39b-49cc-835c-39bb4982c607 | Review W-C-S012 - Resolve all open questions in the BDec W-C-S012 rewrite (M) |  | Text | 0 | 2 | Brian | Square | 3819 | 500 | 3. In Work - High Prio | shape | Jordan Conley | Brian Dec |  |  | 2020-Jan-06 06:53:24
d6878255-7818-431a-9efc-e6828da0fd84 | Coordinate w/ Risk Management (S) |  | Text | 0 | 2 | Brian | Square | 3578 | 828 | 3. In Work - Med Prio | shape | Jordan Conley | Brian Dec |  |  | 2020-Jan-06 06:53:24
8deb8a51-275a-4cdd-afde-c81ce6477707 | Guidance Doc ¦ Use Spec - Outline (S) |  | Text | 0 | 1 | Jordan | Square | 2849 | 1053 | 3. In Work - Med Prio | shape | Joy Iaconianni | Jordan Conley |  |  | 2020-Jan-07 01:02:06
d3ba1440-496b-4727-b01b-e0d7665a50a6 | Guidance Doc - Req't Map - Outline (S) |  | Text | 0 | 0 | Jordan | Square | 3068 | 1053 | 3. In Work - Med Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-10 07:32:54
842d1f1d-4f58-48db-884e-11639a7cfc77 | Guidance Doc - Procedure Map - Compare w/ W-C-S062 and outline (S) |  | Text | 0 | 1 | Jordan | Square | 3309 | 1057 | 3. In Work - Med Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-06 06:53:25
a65c7e68-6886-4406-836f-d6b57efff791 | Learn Jonathan's RTM Validator Tool (L) |  | Text | 0 | 2 | Joy | Square | 3576 | 1061 | 3. In Work - Med Prio | shape | Jordan Conley | Joy Iaconianni |  |  | 2020-Jan-06 06:53:25
fcb62363-47a4-439e-b48d-96367eae82f4 | Update L2 Makeup Slides and publish on Radius (S) |  | Text | 0 | 0 | Gwen | Square | 3763 | 1370 | 3. In Work - Low Prio | shape | Gwen Grant | Gwen Grant |  |  | 2020-Jan-08 08:44:17
03af4e5b-d4e2-4bfc-8707-8f23e123211b | Make changes to documents in FROM folder (F&DR) (L) |  | Text | 0 | 0 | Joy | Gem | 4250 | 282 | Review - High Prio | shape | Joy Iaconianni | Joy Iaconianni |  |  | 2020-Jan-14 01:57:14
3f594384-40fc-46dd-a19c-5d22dab251d9 | Draft Use Spec section of W-C-S012 (M) |  | Text | 0 | 0 | Jordan | Gem | 4250 | 830 | Review - Med Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-16 01:42:11
dcb08e04-3ed6-4f8a-81b0-67b85a985aa0 | Draft Roebling tab on Radius. Migrate info and retire Roebling external site (S) |  | Text | 0 | 0 | Joy | Square | 4250 | 1074 | Review - Med Prio | shape | Jordan Conley | Joy Iaconianni |  |  | 2020-Jan-08 08:45:09
1f60fb66-d055-43c3-b72e-08c035a26fda | Guidance Doc ¦ Outline VRS documentation for internal review (M) |  | Text | 0 | 1 | Sol | Square | 5055 | 274 | Done - High Prio | shape | Jordan Conley | Sol Posada |  |  | 2020-Jan-06 06:53:49
f9c76287-8e46-4937-b3e5-9a0e31b65994 | Finalize "Essential Needs" Examples for PEC Review (M) |  | Text | 0 | 0 | Team Member | Square | 5314 | 280 | Done - High Prio | shape | Jordan Conley | Jan Valenzuela |  |  | 2020-Jan-07 04:33:08
7b5d7992-7701-4ba8-8f02-ea9f4562cb33 | Finalize "Essential Needs" Definition (Phase 1) for PEC Review (M) |  | Text | 0 | 3 | Team Member | Square | 5550 | 282 | Done - High Prio | shape | Jordan Conley | Jan Valenzuela |  |  | 2020-Jan-06 06:53:25
feb3db3c-7f4b-425d-9a83-366ed40fd5a5 | Implementation Plan/ Milestone Chart (M) |  | Text | 0 | 1 | Gwen | Square | 5075 | 536 | Done - High Prio | shape | Jordan Conley | Gwen Grant |  |  | 2020-Jan-06 06:53:24
b4a5df17-8264-49d0-9670-b1ab66466b96 | PLT Presentation (M) |  | Text | 0 | 0 | Gwen | Gem | 5083 | 532 | Done - High Prio | shape | Jordan Conley | Gwen Grant |  |  | 2020-Jan-10 06:51:40
830e5ee7-b094-4694-a6cf-c4399fbc2489 | DMADVV Process Map (L) |  | Text | 3 | 0 | Gwen | Square | 5055 | 538 | Done - High Prio | shape | Jordan Conley | Gwen Grant |  |  | 2020-Jan-06 06:53:24
7c7d5a09-cc4e-4f79-a22d-e497ad53a53c | Support Pelvis team with Val labs (S) |  | Text | 0 | 0 | Brian | Gem | 5550 | 538 | Done - High Prio | shape | Jordan Conley | Brian Dec |  |  | 2020-Jan-16 01:52:19
0c5810cc-0024-41f6-8f5d-d4534f9c5350 | Identify Extended Review Team for Roebling Tools (S) |  | Text | 0 | 1 | Gwen | Square | 5569 | 828 | Done - Med Prio | shape | Jordan Conley | Gwen Grant |  | 2020-Jan-08 | 2020-Jan-06 06:53:24
7b0d27e6-0b33-42d3-ba84-ae03fac281dc | Post Charter Process Map - VRS (S) |  | Text | 0 | 0 | Sol | Square | 5081 | 839 | Done - Med Prio | shape | Joy Iaconianni | Sol Posada |  |  | 2020-Jan-07 01:02:20
a9d02961-ef61-4c97-b2e8-56b1309612ee | Set up Future PEC Steering Committee Meetings (M) |  | Text | 0 | 0 | Gwen | Square | 5346 | 837 | Done - Med Prio | shape | Gwen Grant | Gwen Grant |  |  | 2020-Jan-08 08:48:59
fe4bf3ef-f544-404c-9f3a-ae3b4575b70b | Roebling Stakeholder Exit Interviews (M) |  | Text | 0 | 2 | Gwen | Square | 5319 | 845 | Done - Med Prio | shape | Jordan Conley | Gwen Grant |  |  | 2020-Jan-06 03:40:58
b9b84d7e-4355-4e32-9646-26688eb17423 | Standard Tool Rollout Plan for 2020 (S) |  | Text | 0 | 0 | Gwen | Square | 5319 | 841 | Done - Med Prio | shape | Jordan Conley | Gwen Grant |  |  | 2020-Jan-07 04:22:34
b9ff6efb-d2bd-4deb-9457-3fa5f47821ca | Standard DEx Tool - SIPOC - Phase 1 (M) |  | Text | 0 | 3 | Joy | Gem | 5332 | 1079 | Done - Med Prio | shape | Joy Iaconianni | Joy Iaconianni |  |  | 2020-Jan-14 01:51:49
cb145e3a-4bfb-4cf6-a192-87a1259aa0c5 | Draft Ankle Fusion with Use Spec and Req't Map (M) |  | Text | 0 | 0 | Jordan | Gem | 5115 | 1085 | Done - Med Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-22 08:27:36
c7400d7e-a468-4149-af74-fe0d8f496768 | Post Charter Process Map - RTM (S) |  | Text | 0 | 1 | Jordan | Square | 5550 | 1089 | Done - Med Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-06 06:53:25
808fded8-f29e-4ddb-b52f-0f46522b2001 | Draft Agenda to cover with VA Clavicle team reconnect meeting (S) |  | Text | 0 | 0 | Jordan | Gem | 5332 | 1369 | Done - Low Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-15 02:25:30
de93e0cd-defd-48e2-9243-81692bb3a9e1 | Mind Map Rollout Plan and align with team (S) |  | Text | 0 | 1 | Jordan | Square | 5550 | 1375 | Done - Low Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-06 06:53:25
7a4bb8ba-4fd8-46e8-a1ab-38bfe3508030 | Kick off NPD R&D Playbook (M) |  | Text | 0 | 0 | Jordan | Square | 5308 | 1597 | Done - Low Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 07:32:32
933ab901-3faa-4b38-8956-90f04282ca13 | Finalize Use Spec Requirements (M) |  | Text | 0 | 2 | Jordan | Square | 5310 | 1603 | Done - Low Prio | shape | Jordan Conley | Jordan Conley |  |  | 2020-Jan-06 06:53:24
390b4357-109c-47ab-bdbc-e837c7333777 | Guidance on transforming CTGs into Design Inputs. |  | Text | 0 | 0 | Jordan | Square | 33 | 1994 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
8c8e2f12-74b8-4df7-8d5f-b0874811d621 | Investigate country specific testing/staggered release; consider decoupling into different RTM sheets. |  | Text | 0 | 0 | Jordan | Square | 245 | 1994 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
71f08ea2-c9b2-4faa-8936-0caae28f50d6 | Writing procedure based FDRs will make it challenging to break out FDRs into several different ones for type of device like Delorean did (requirements are too intertwined). Will this be accepted? |  | Text | 0 | 0 | Jordan | Square | 457 | 1994 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
b9cdf08f-c285-410c-a41b-a9af209d0e73 | Rationale for User Need / DI / DS: Guidance on how to write – what do well written examples look like? Including Business Needs. Maxframe question: What level of scrutiny will be expected from approvers (and eventual auditors) about the statements made in the Rationale field? Will there need to be evidence to support? |  | Text | 0 | 0 | Jordan | Square | 669 | 1994 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
cfbe8165-9cf2-47c1-86a2-94ad22b173af | Val / Ver Strategy: Guidance on how to write – what do well written examples look like? |  | Text | 0 | 0 | Jordan | Square | 881 | 1994 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
5d72d933-f1a4-4deb-a299-1289d45117ac | What is the required input to RC from VOC? What is required to be in the VOC summary? |  | Text | 0 | 0 | Jordan | Square | 1093 | 1994 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
24d01553-47a6-40ab-bc56-6bf1eab61029 | "Functional Analysis" tool - is this in the RC workstream to produce, or is that PPS? Or has this evolved into the TFS now? |  | Text | 0 | 0 | Jordan | Square | 1305 | 1994 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
88efb0f2-b905-4897-9ce6-9458e40043c9 | Do we need a standard way to address compatibility requirements between new device to new device + new device to existing device? |  | Text | 0 | 0 | Jordan | Square | 33 | 2206 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
9a2d3d0a-e390-4f48-af26-a046b03c900c | Agree on arrangement of W-C-S012: Appendix approach for Roebling process, or separate work instruction? |  | Text | 0 | 0 | Jordan | Square | 245 | 2206 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
7a3dc1d9-01d5-4822-8e28-ae122be16f20 | Resolve all open questions in the BDec Roebling Outline |  | Text | 0 | 0 | Jordan | Square | 457 | 2206 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
2bccd4d2-7f1c-4eac-858f-fa42820914b9 | Automated data transfer of RTM into VRS |  | Text | 0 | 1 | Sol | Square | 669 | 2206 | Ideas - Stories to be defined | magnetic | Jordan Conley | Sol Posada |  |  | 2020-Jan-07 04:38:33
19f773ef-00ca-4bb0-936a-ae26abbd7c04 | Claims associated with the new device are spread throughout the 4 categories: we need a way to track/highlight them in the matrix for evidence generation. |  | Text | 0 | 0 | Jordan | Square | 881 | 2206 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
35301633-1709-42a0-8ff6-60c9b9c5c4bd | Investigate: How does Evidence Generation (HEMA) feed into V&V - Topic: Decomplexity. |  | Text | 0 | 0 | Jordan | Square | 1093 | 2206 | Ideas - Stories to be defined | magnetic | Jordan Conley | Jordan Conley |  |  | 2020-Jan-07 02:38:13
6f0a6877-55df-4ee7-80ed-9a85e395e392 | Roebling Update Communication (M) |  | Text | 0 | 1 | Gwen | Square | 1545 | 1994 | Can't start until... | magnetic | Gwen Grant | Gwen Grant |  |  | 2020-Jan-08 07:08:56
86e00723-ac2c-453a-b45b-8ac4dbaf85f3 | Conjoint Analysis Part 2 - release |  | Text | 0 | 1 | Joy | Square | 1757 | 1994 | Can't start until... | magnetic | Joy Iaconianni | Joy Iaconianni |  |  | 2020-Jan-07 01:02:55
6dd5f8db-23ad-469f-847d-8cd17b8e591c | 1. Summarize task on regular sticky |  | Text | 0 | 0 | Team Member | Title | 4137 | 1994 | Scrum Board Guidelines on Stormboard | magnetic | Jordan Conley |  |  |  | 2020-Jan-06 09:14:00
5988432d-7300-4756-ba78-ce6dbe41ed06 | 2. Color code to legend and ALSO assign owner (click on bottom right of sticky) |  | Text | 0 | 0 | Team Member | Title | 4349 | 1994 | Scrum Board Guidelines on Stormboard | magnetic | Jordan Conley |  |  |  | 2020-Jan-06 09:22:10
c26a8c3f-3093-4610-bf5e-edf3c9bba410 | 3. Suggest using Comments to capture substeps or notes (OR can use Index Cards to capture substeps) Use @ to tag another team member |  | Text | 0 | 0 | Team Member | Title | 4561 | 1994 | Scrum Board Guidelines on Stormboard | magnetic | Jordan Conley |  |  |  | 2020-Jan-06 09:12:41
efc2012d-3235-4ac3-828d-eca60c61c8dd | 4. Arrange in Matrix of priority (low/high) and size (small, medium, large) |  | Text | 0 | 0 | Team Member | Title | 4985 | 1994 | Scrum Board Guidelines on Stormboard | magnetic | Jordan Conley |  |  |  | 2020-Jan-06 09:29:18
44230899-caeb-4522-bf9c-e265ccce1faa | 5. Use "Gem" shaped Stickies for new stories added during Sprint |  | Text | 0 | 0 | Team Member | Title | 5197 | 1994 | Scrum Board Guidelines on Stormboard | magnetic | Joy Iaconianni |  |  |  | 2020-Jan-21 06:49:06
ba2f8b29-d47c-45eb-8eaa-150499485fe1 | 6. Move stories from 'Done' to 'Archive' proceeding to next sprint |  | Text | 0 | 0 | Team Member | Title | 5409 | 1994 | Scrum Board Guidelines on Stormboard | magnetic | Joy Iaconianni |  |  |  | 2020-Jan-23 03:40:00
bc3639fb-62b7-480d-8107-01e5231bb74a | Link to Excel Tracking Report: https://jnj.sharepoint.com/:x:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B4AECE9EB-1B3F-41E1-85A3-495ABA4CED58%7D&file=Roebling%20Backlog%20and%20Sprint%20Plans.xlsx&action=default&mobileredirect=true |  | Text | 0 | 0 | Team Member | Title | 1305 | -264 |  | default | Jordan Conley |  |  |  | 2020-Jan-07 01:53:51
670bc3c5-0f2c-4bec-9ce9-60869e9ce2e6 | Link to Milestone Schedule: https://jnj.sharepoint.com/:p:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B10B1C622-4411-4698-95C7-7E91EF5E9AFB%7D&file=DRAFT%20Milestone%20Schedule%20-%20Q1%202020.pptx&action=edit&mobileredirect=true |  | Text | 0 | 0 | Team Member | Title | 1820 | -264 |  | default | Jordan Conley |  |  |  | 2020-Jan-23 02:04:09
70facec2-0473-4611-ac7f-eab62241e753 | Link to RTM Questions: https://jnj.sharepoint.com/:x:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B9AC12DF1-1D71-4DBB-9A8F-E770B9821D1E%7D&file=Req%20Cascade%20Questions%20to%20Answer.xlsx&action=default&mobileredirect=true |  | Text | 0 | 0 | Brian | Title | -177 | 2063 |  | default | Jordan Conley |  |  |  | 2020-Jan-07 02:43:26

## Comments
Idea | Storm / Substorm | Commenter | Date | Comment | Idea Identifier
WI Update Planning | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-08 19:25 | TASKS: 1. Determine complete list of WI impacted by Roebling 2. Request a PD Prep "APB" for anticipated changes to related WI across the org on the horizon 3. Determine Adaptive Access Ned 4. Coordinate upcoming PD Prep agendas to include Roebling (US and EU) 5. Validate intended WI changes across Roebling (internal) 6. Draft outline "Impact Assessments" (stakeholder and change) 7. Coordinate with Windchill for the RTM (Jonathan/.John T.) | d3c15d51-0b59-45da-a8c8-24f7f62b3242
Guidance Doc ¦ Req Map - Draft | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:09 | 1. AA 2. BB 3. CC | aed04b18-f66f-4778-8299-3cb615aaef29
US Q4 Workshop ¦ RTM Transition | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-08 19:26 | TASKS: 1. Initiate conversation with Brian Smith and David 2. Meet internally to determine which NPD team to partner to build this collateral | 502439fa-e4d1-4667-9027-1aa53050a2ff
Create Common Use Survey for L3 Partners | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-08 19:32 | TASKS: 1. Draft end user training survey (i.e. MS Forms) - TBD 2. Review draft survey internally with Leads and Gwen to finalize - TBD 3. Finalize based on feedback shared - TBD 4. Include in the kickoff presentations with each L3 Training partner - TBD | f2dac4ab-077d-41e0-8e89-c5c0d4afd3fc
Weibull Stat Guidance | Roebling Scrum Board - Sprint 13 | Paul Scilingo | 2020-01-23 13:14 | Target: February release | a7f079ed-36b1-4550-9d16-f09ddc069da5
L3 Training Dry Run w/ Ankle Fusion | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:22 | 1. Present Roebling Process Map (Pre-Charter) - 11/22 2. Draft Use Spec for Ankle Fusion - Jordan to send to AF Team 3. Draft Requirement Map to prep for CTG Roadmap - Jordan | 86a032a7-5516-4bff-b15c-c50640d7c716
CORe 3 of 6 ¦ Labeling (Gen1 Solution) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-08 19:37 | TASKS: 1. Draft requirements for each; User Need, Source of Need, Design Input, and Design Output 2. Determine mutual agreement for requirements: UN, SN, DI, and DO 3. Document V&V Deliverables; how will each of these fulfill our specifications | e14a2ff6-b28b-4c58-a6b0-59242f7a250e
Req. Spec. ¦ Procedure Based FDR vs. Device Specific | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-08 19:40 | TASKS: 1. AA 2. BB | 1fa9922c-0b34-4d81-8512-e7f7db462eb6
CORe 3 of 6 ¦ Packaging (Gen1 Solution) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-08 19:34 | TASKS: 1. Determine mutually agreed requirements; User Need, Source of Need, Design Input, and Design Output 2. Document V&V Deliverables; how will each of these fulfill our specifications | 79bc2bb2-942f-4bbd-a7fe-8a01516c3652
DMD Assessment for L3 Training | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:23 | 1. Meeting w/ Mario on 12/18 to see what/if any next steps | d884a657-00e3-4b7b-b59a-87ecbb74fec0
Req. Spec. ¦ Part Number to Requirement Traceability | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-08 19:39 | TASKS: 1. TBD 2. Investigate benefits of "Generic Device Type" concept | dbf38b19-18e4-4d06-9ff4-52c54e2e925a
CORe 3 of 6 ¦ Bio Comp (Gen1 Solution) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-08 19:39 | TASKS: 1. Determine mutually agreed requirements; User Need, Source of Need, Design Input, and Design Output 2. Document V&V Deliverables; how will each of these fulfill our specification(s) | 9fdd6eea-ec6d-4f34-b251-e1d7b9aff46a
Standard DEx Tool - Stakeholder Analysis - Phase 1 (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-14 13:54 | for March 30 rollout | 2cf5501e-5d90-4e9d-82ed-71b13a04584e
Standard DEx Tool - Multi-Generational Plan - Phase 1 (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-14 13:54 | for March 30 rollout | 7d4bfe1f-087f-42d2-91cb-3be39f282698
Standard DEx Tool - Multi-Generational Plan - Phase 1 (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-14 13:54 | partner with PjM | 7d4bfe1f-087f-42d2-91cb-3be39f282698
RTM ¦ External Parts List | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:12 | 1. Better understand the EPL; do US teams even rely on EPLs? What info is captured? 2. Pressure test combining EPL with RTM for a minimum of 2-3 projects | b253a17d-8453-440b-ad09-922f069efe8c
RTM ¦ External Parts List | Roebling Scrum Board - Sprint 13 | Jordan Conley | 2020-01-07 14:45 | From RTM questions to be answered: How to leverage the “External Parts List” for the devices in scope of the RTM. Can it be the same list? Also we just need to finalize the Parts List process in general for the RTM. https://jnj.sharepoint.com/:x:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B9AC12DF1-1D71-4DBB-9A8F-E770B9821D1E%7D&file=Req%20Cascade%20Questions%20to%20Answer.xlsx&action=default&mobileredirect=true | b253a17d-8453-440b-ad09-922f069efe8c
CORe 3 of 6 ¦ F&DR S5 (Gen1 Solution) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-08 19:38 | TASKS: 1. Determine mutually agreed requirements; User Need, Source of Need, Design Input, and Design Output 2. Document V&V Deliverables; how will each of these fulfill our specification(s) | 2297942d-ad75-440d-975b-93d12d6c4a53
Partner 7 of n ¦Maxframe Pilot | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:21 | 1. Next meeting is Wed. 11/20 2. B. Dec to review RTM file and select a few user need lines to bring to the latest template 3. Next session - as a team, work through the lines to get complete cascades for all levels. 4. Continue with one more session with Joe (12/10) to review remaining RTM lines for Schantz 5. B. Dec to summarize key learnings to feed into procedure, guidance, and training 6. Review internally with RC Team | 97a5d209-6cdb-4c8d-83d6-26f4d38f52cf
Guidance Doc ¦ RTM | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:07 | 1. AA 2. BB 3. CC | 556c3852-9ba3-474b-b03b-4f40d1b8be94
RTM ¦ Windchill Readiness | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:28 | 1. Conduct follow up meeting with Windchill POCs (JPrete and RFehnel) - TBD 2. Determine limitations for maintaining a MS Excel document in Windchill 3. Identify recommended approach for maintaining the RTM file in Windchill 4. Determine process for releasing and maintaining RTM in Windchill | d99a3db6-f0a3-4846-a784-a61b7cfb2a4e
RTM ¦ Windchill Readiness | Roebling Scrum Board - Sprint 13 | Jordan Conley | 2020-01-07 14:49 | From RC questions to be answered: Windchill report functionality (printability with Windchill). What can be built into the template by default to ensure it prints in a readable manner? https://jnj.sharepoint.com/:x:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B9AC12DF1-1D71-4DBB-9A8F-E770B9821D1E%7D&file=Req%20Cascade%20Questions%20to%20Answer.xlsx&action=default&mobileredirect=true | d99a3db6-f0a3-4846-a784-a61b7cfb2a4e
Req. Spec ¦ Draft "How to write V&V Strategy" (S) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 12:43 | 1. Propose options for minimum level of detail contained in a well written strategy 2. Create well written examples to be included in RTM Guidance Doc 3. Confirm internally the examples intended for use in RTM Guidance Doc | 54534f13-fc63-4b8b-8309-2ade3e698444
Coordinate w/ TPP workstream in Scope TTM (S) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:16 | 1. Meet w/ TPP workstream to confirm the definition of CTG as an input to Roebling 2. Update Glossary and Guidance Doc as necessary | ddfc35e8-05f7-4242-b5e4-7fa8ee7f137e
Draft CA - Complete Remaining Redlines (M) | Roebling Scrum Board - Sprint 13 | Jordan Conley | 2020-01-06 20:47 | Initial redlines of W-C-S012 & 676 are available. | cad5771d-e7d8-4239-8b38-8b56f079c41b
Draft CA - Complete Remaining Redlines (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 12:47 | 1. upload affected items/redlines for primary CA | cad5771d-e7d8-4239-8b38-8b56f079c41b
Finalize & Post TFS Guidance (L) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 12:55 | 1. Review internally with Gwen (other leads?) - TBD 2. Refine based on internal feedback - TBD 3. Share w/ extended review team - TBD 3. Post centrally (via Radius) - TBD 4. Send announcement across org of the tool's availability - TBD | 696bb571-3022-400a-8ad0-22f8e554fb44
Guidance Doc ¦ Dex - Develop Outline (L) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 12:50 | 1. Draft guidance documentation based on an end user (NPD team member) - NPD 2. Review Internally with deliverable owners (Brian, Jordan, and Sol) - TBD 3. Refine based on internal feedback - TBD 4. Share externamlly - who? (PMO, Quality, others?) | b86d5231-1d10-43ae-b83f-e792d5580344
Convert Roebling (676) Process outline into 012 appendix 1 (L) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-06 20:29 | 1. Close all open questions, action items related to RC 2. Use outline as starting point for writing the document | 40dedc17-5060-4686-a80d-ff8aef3e2778
Review W-C-S012 - Resolve all open questions in the BDec W-C-S012 rewrite (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 12:52 | 1. Consider logistics of how new Roebling procedure/form are worked into existing wording 2. Highlight areas that will need to change 3. Create redlines for W-C-S012 to adapt the new Roebling information | ca87be64-b39b-49cc-835c-39bb4982c607
Review W-C-S012 - Resolve all open questions in the BDec W-C-S012 rewrite (M) | Roebling Scrum Board - Sprint 13 | Brian Dec | 2020-01-14 19:00 | Updated list: 1. Discuss and resolve open questions/comments within Roebling team. 2. Follow up with Brian Smith on remaining open topics. | ca87be64-b39b-49cc-835c-39bb4982c607
Coordinate w/ Risk Management (S) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:26 | 1. Identify next steps: outline framework for guidance doc 2. Check in w/ David scheduled for 12/4 to review above and determine next steps 3. David to enter TFNA - THE requirements in the RTM 4. David to pilot his Risk Process flow with several reqs from his TFNA- THE project *start to finish* 5. David to identify connection points between risk and Roebling RC process 6. Determine if this sample is sufficient to use for end user guidance | d6878255-7818-431a-9efc-e6828da0fd84
Coordinate w/ Risk Management (S) | Roebling Scrum Board - Sprint 13 | Brian Dec | 2020-01-14 18:58 | Updated steps: 1. Complete initial draft of RTM procedural steps without essential/core requirements. – Main task but may extend as it’s developed. 2. Begin alignment with R&D on strategy to align the new RTM draft to the current DCRM Draft for the project (i.e. we have changed the first column in the FDR which has historically been the first column in the DCRM. The question here is how do these line up now to the RTM) 3. Identify 1 or 2 possible Needs that align to the DCRM for baseline examples in future guidance document. | d6878255-7818-431a-9efc-e6828da0fd84
Guidance Doc ¦ Use Spec - Outline (S) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:10 | 1. AA 2. BB 3. CC | 8deb8a51-275a-4cdd-afde-c81ce6477707
Guidance Doc - Procedure Map - Compare w/ W-C-S062 and outline (S) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 12:45 | 1. AA 2. BB 3. CC | 842d1f1d-4f58-48db-884e-11639a7cfc77
Learn Jonathan's RTM Validator Tool (L) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:15 | 1. learn basics of Python language 2. investigate tool functionality 3. Reach out to Jonathan as needed | a65c7e68-6886-4406-836f-d6b57efff791
Learn Jonathan's RTM Validator Tool (L) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-21 13:18 | Determine benchmarks for this task | a65c7e68-6886-4406-836f-d6b57efff791
Guidance Doc ¦ Outline VRS documentation for internal review (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 12:47 | 1. Draft Guidance doc based on an end user (NPD team member) - 11/22 2. Review internally with Gwen - TBD | 1f60fb66-d055-43c3-b72e-08c035a26fda
Finalize "Essential Needs" Definition (Phase 1) for PEC Review (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 12:46 | 1. Integrate final definition and rules into Manefesto Guidance | 7b5d7992-7701-4ba8-8f02-ea9f4562cb33
Finalize "Essential Needs" Definition (Phase 1) for PEC Review (M) | Roebling Scrum Board - Sprint 13 | Jordan Conley | 2020-01-07 14:51 | RC Question to be answered: How to address Risk related "Essential Needs" in the cascade / new procedure? Includes Lifetime / Reliability for instruments. https://jnj.sharepoint.com/:x:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B9AC12DF1-1D71-4DBB-9A8F-E770B9821D1E%7D&file=Req%20Cascade%20Questions%20to%20Answer.xlsx&action=default&mobileredirect=true | 7b5d7992-7701-4ba8-8f02-ea9f4562cb33
Finalize "Essential Needs" Definition (Phase 1) for PEC Review (M) | Roebling Scrum Board - Sprint 13 | Jordan Conley | 2020-01-07 16:26 | Task: Consult with DQ and Principal Engineering Committee (next sprint). Look at Brian's feedback including RTM | 7b5d7992-7701-4ba8-8f02-ea9f4562cb33
Implementation Plan/ Milestone Chart (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 12:42 | 1. Tool Leads to provide input before 11/20 Team Meeting 2. Revisit Lead input/feedback during 11/20 Wkly Team Meeting - 11/20 3. Follow up/resulting actions from the Team Meeting 11/22 | feb3db3c-7f4b-425d-9a83-366ed40fd5a5
Identify Extended Review Team for Roebling Tools (S) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:19 | 1. Identify target Contacts (up to 5) - Gwen 2. Connect to request availability to support - Gwen 3. Finalize list of extended review team - Gwen 4. Coordinate expected timeline (per anticipated tool availability) - Gwen | 0c5810cc-0024-41f6-8f5d-d4534f9c5350
Roebling Stakeholder Exit Interviews (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-06 20:28 | 1. Determine list of original attendees 2. Schedule interviews with each applicable stakeholder 3. Conduct exits | fe4bf3ef-f544-404c-9f3a-ae3b4575b70b
Roebling Stakeholder Exit Interviews (M) | Roebling Scrum Board - Sprint 13 | Jordan Conley | 2020-01-07 16:10 | Blocker: I can' get time with Rob | fe4bf3ef-f544-404c-9f3a-ae3b4575b70b
Standard DEx Tool - SIPOC - Phase 1 (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-14 13:53 | for Feb 18 Rollout | b9ff6efb-d2bd-4deb-9457-3fa5f47821ca
Standard DEx Tool - SIPOC - Phase 1 (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-16 13:24 | TASKS: 1. ask Gwen for SIPOC Lunch & Learn Slide Deck | b9ff6efb-d2bd-4deb-9457-3fa5f47821ca
Standard DEx Tool - SIPOC - Phase 1 (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-23 13:36 | Sprint 14: Phase 2 Get example/feedback from users of the tool | b9ff6efb-d2bd-4deb-9457-3fa5f47821ca
Post Charter Process Map - RTM (S) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:31 | 1. Tool leads to provide updates to the StormBoard - TBD 2. Draft MS Visio version of the combined process map - TBD 3. Review internally (Roebling Team) - TBD 4. Update/finalize combined Post Charter MS Visio Roebling Process Map - TBD | c7400d7e-a468-4149-af74-fe0d8f496768
Mind Map Rollout Plan and align with team (S) | Roebling Scrum Board - Sprint 13 | Jordan Conley | 2020-01-06 19:44 | 1. Meet with Gwen & Brian 2. Define criteria for access 3. Define license management process | de93e0cd-defd-48e2-9243-81692bb3a9e1
Finalize Use Spec Requirements (M) | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:29 | 1. Get feedback for review from Dan O'Connor 2. Finalize template based on what Ankle Fusion team is using 3. Meet with Kevin (AF) to confirm final template | 933ab901-3faa-4b38-8956-90f04282ca13
Finalize Use Spec Requirements (M) | Roebling Scrum Board - Sprint 13 | Jordan Conley | 2020-01-07 14:53 | RC Question to be answered: Finalize Use Specification document – how does it fit into the process? best practice example? For what gate or design review? https://jnj.sharepoint.com/:x:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B9AC12DF1-1D71-4DBB-9A8F-E770B9821D1E%7D&file=Req%20Cascade%20Questions%20to%20Answer.xlsx&action=default&mobileredirect=true | 933ab901-3faa-4b38-8956-90f04282ca13
Automated data transfer of RTM into VRS | Roebling Scrum Board - Sprint 13 | Sol Posada | 2020-01-09 19:12 | Software Requirements: https://jnj.sharepoint.com/teams/Roebling2/Shared%20Documents/Performance%20Prediction/10.0%20Verification%20Readiness%20Scorecard/20191106%20RTM%20Integration.docx?web=1 | 2bccd4d2-7f1c-4eac-858f-fa42820914b9
Roebling Update Communication (M) | Roebling Scrum Board - Sprint 13 | Gwen Grant | 2020-01-08 19:21 | Milestone chart should be part of this communication | 6f0a6877-55df-4ee7-80ed-9a85e395e392
Conjoint Analysis Part 2 - release | Roebling Scrum Board - Sprint 13 | Joy Iaconianni | 2020-01-07 13:10 | 1. Request review/input from Marketing on the Tool/Guidance - TBD - Gwen 2. Finalize tool and associated guidance per feedback received - TBD - Joy 3. Post to Radius when complete - TBD - Joy 4. Send email announcement to the org when available on Radius - TBD - Gwen | 86e00723-ac2c-453a-b45b-8ac4dbaf85f3

## Chat
Date | By | Message

## Connectors
From | To | Direction | Color | Label | Storm | From Identifier | To Identifier
Rationale for User Need / DI / DS: Guidance on how to write – what do well written examples look like? Including Business Needs. Maxframe question: What level of scrutiny will be expected from approvers (and eventual auditors) about the statements made in the Rationale field? Will there need to be evidence to support? | Val / Ver Strategy: Guidance on how to write – what do well written examples look like? | To | Default |  | Roebling Scrum Board - Sprint 13 | b9cdf08f-c285-410c-a41b-a9af209d0e73 | cfbe8165-9cf2-47c1-86a2-94ad22b173af
Post Charter Process Map - VRS (S) | DMADVV Process Map (L) | To | Default |  | Roebling Scrum Board - Sprint 13 | 7b0d27e6-0b33-42d3-ba84-ae03fac281dc | 830e5ee7-b094-4694-a6cf-c4399fbc2489
Post Charter Process Map - RTM (S) | DMADVV Process Map (L) | To | Default |  | Roebling Scrum Board - Sprint 13 | c7400d7e-a468-4149-af74-fe0d8f496768 | 830e5ee7-b094-4694-a6cf-c4399fbc2489
Make changes to documents in FROM folder (F&DR) (L) | Draft CA - Complete Remaining Redlines (M) | To | Default |  | Roebling Scrum Board - Sprint 13 | 03af4e5b-d4e2-4bfc-8707-8f23e123211b | cad5771d-e7d8-4239-8b38-8b56f079c41b
Update L2 Makeup Slides and publish on Radius (S) | Draft Roebling tab on Radius. Migrate info and retire Roebling external site (S) | To | Default |  | Roebling Scrum Board - Sprint 13 | fcb62363-47a4-439e-b48d-96367eae82f4 | dcb08e04-3ed6-4f8a-81b0-67b85a985aa0
Guidance Doc ¦ Use Spec - Outline (S) | Guidance Doc - Req't Map - Outline (S) | To | Default |  | Roebling Scrum Board - Sprint 13 | 8deb8a51-275a-4cdd-afde-c81ce6477707 | d3ba1440-496b-4727-b01b-e0d7665a50a6
Guidance Doc - Req't Map - Outline (S) | Guidance Doc - Procedure Map - Compare w/ W-C-S062 and outline (S) | To | Default |  | Roebling Scrum Board - Sprint 13 | d3ba1440-496b-4727-b01b-e0d7665a50a6 | 842d1f1d-4f58-48db-884e-11639a7cfc77
Draft Use Spec section of W-C-S012 (M) | Review W-C-S012 - Resolve all open questions in the BDec W-C-S012 rewrite (M) | To | Default |  | Roebling Scrum Board - Sprint 13 | 3f594384-40fc-46dd-a19c-5d22dab251d9 | ca87be64-b39b-49cc-835c-39bb4982c607

## Tasks
Task | Due Date | Date Completed | Date Assigned | Assigned To | Status
Convert Roebling (676) Process outline into 012 appendix 1 (L) |  |  | 2020-01-06 | Brian Dec | Assigned
Roebling Stakeholder Exit Interviews (M) |  |  | 2020-01-06 | Gwen Grant | Assigned
DMADVV Process Map (L) |  |  | 2020-01-06 | Gwen Grant | Assigned
Identify Extended Review Team for Roebling Tools (S) |  | 2020-01-08 | 2020-01-06 | Gwen Grant | Complete
Req. Spec ¦ Draft &quot;How to write V&amp;V Strategy&quot; (S) |  |  | 2020-01-06 | Brian Dec | Assigned
Guidance Doc ¦ Outline VRS documentation for internal review (M) |  |  | 2020-01-06 | Sol Posada | Assigned
Draft CA - Complete Remaining Redlines (M) |  |  | 2020-01-06 | Jordan Conley | Assigned
Guidance Doc ¦ Dex - Develop Outline (L) |  |  | 2020-01-06 | Gwen Grant | Assigned
Finalize Use Spec Requirements (M) |  |  | 2020-01-06 | Jordan Conley | Assigned
Learn Jonathan&#039;s RTM Validator Tool (L) |  |  | 2020-01-06 | Joy Iaconianni | Assigned
Coordinate w/ Risk Management (S) |  |  | 2020-01-06 | Brian Dec | Assigned
Review W-C-S012 - Resolve all open questions in the BDec W-C-S012 rewrite (M) |  |  | 2020-01-06 | Brian Dec | Assigned
Mind Map Rollout Plan and align with team (S) |  |  | 2020-01-06 | Jordan Conley | Assigned
Implementation Plan/ Milestone Chart (M) |  |  | 2020-01-06 | Gwen Grant | Assigned
L3 Training Dry Run w/ Ankle Fusion |  |  | 2020-01-06 | Jordan Conley | Assigned
Post Charter Process Map - RTM (S) |  |  | 2020-01-06 | Jordan Conley | Assigned
Guidance Doc - Procedure Map - Compare w/ W-C-S062 and outline (S) |  |  | 2020-01-06 | Jordan Conley | Assigned
Finalize &amp; Post TFS Guidance (L) |  |  | 2020-01-06 | Sol Posada | Assigned
Finalize &quot;Essential Needs&quot; Definition (Phase 1) for PEC Review (M) |  |  | 2020-01-06 | Jan Valenzuela | Assigned
Post Charter Process Map - VRS (S) |  |  | 2020-01-07 | Sol Posada | Assigned
Partner 7 of n ¦Maxframe Pilot |  |  | 2020-01-07 | Brian Dec | Assigned
DMD Assessment for L3 Training |  |  | 2020-01-07 | Brian Dec | Assigned
Marketing Claims |  |  | 2020-01-07 | Brian Dec | Assigned
Conjoint Analysis Part 2 - release |  |  | 2020-01-07 | Joy Iaconianni | Assigned
RTM ¦ Windchill Readiness |  |  | 2020-01-07 | Jordan Conley | Assigned
RTM ¦ External Parts List |  |  | 2020-01-07 | Jordan Conley | Assigned
Guidance Doc ¦ RTM |  |  | 2020-01-07 | Jordan Conley | Assigned
Standard Tool Rollout Plan for 2020 (S) |  |  | 2020-01-07 | Gwen Grant | Assigned
Finalize &quot;Essential Needs&quot; Examples for PEC Review (M) |  |  | 2020-01-07 | Jan Valenzuela | Assigned
Coordinate w/ TPP workstream in Scope TTM (S) |  |  | 2020-01-07 | Gwen Grant | Assigned
Kick off NPD R&amp;D Playbook (M) |  |  | 2020-01-07 | Jordan Conley | Assigned
Create L3 Training Content |  |  | 2020-01-08 | Sol Posada | Assigned
Implementation Execution ¦ L3 Training TBD |  |  | 2020-01-08 | Gwen Grant | Assigned
Implementation Execution ¦ L3 Training TFS |  |  | 2020-01-08 | Sol Posada | Assigned
Draft Roebling tab on Radius. Migrate info and retire Roebling external site (S) |  |  | 2020-01-08 | Joy Iaconianni | Assigned
Standard DEx Tool - SIPOC - Phase 1 (M) |  |  | 2020-01-14 | Joy Iaconianni | Assigned
Standard DEx Tool - Multi-Generational Plan - Phase 1 (M) |  |  | 2020-01-14 | Joy Iaconianni | Assigned
Standard DEx Tool - Stakeholder Analysis - Phase 1 (M) |  |  | 2020-01-14 | Joy Iaconianni | Assigned
Make changes to documents in FROM folder (F&amp;DR) (L) |  |  | 2020-01-14 | Joy Iaconianni | Assigned
WI Update Planning |  |  | 2020-01-16 | Jordan Conley | Assigned
CORe 3 of 6 ¦ Labeling (Gen1 Solution) |  |  | 2020-01-16 | Jan Valenzuela | Assigned
CORe 3 of 6 ¦ Bio Comp (Gen1 Solution) |  |  | 2020-01-16 | Jan Valenzuela | Assigned
CORe 3 of 6 ¦ Packaging (Gen1 Solution) |  |  | 2020-01-16 | Jan Valenzuela | Assigned
Req. Spec. ¦ Procedure Based FDR vs. Device Specific |  |  | 2020-01-16 | Brian Dec | Assigned
Guidance Doc ¦ Writing Good Requirements |  |  | 2020-01-16 | Brian Dec | Assigned
CORe 3 of 6 ¦ F&amp;DR S5 (Gen1 Solution) |  |  | 2020-01-16 | Jan Valenzuela | Assigned
Req. Spec. ¦ Part Number to Requirement Traceability |  |  | 2020-01-16 | Brian Dec | Assigned
Support Pelvis team with Val labs (S) |  |  | 2020-01-16 | Brian Dec | Assigned
PLT Presentation (M) |  |  | 2020-01-22 | Gwen Grant | Assigned
Set up Future PEC Steering Committee Meetings (M) |  |  | 2020-01-22 | Gwen Grant | Assigned
Draft Agenda to cover with VA Clavicle team reconnect meeting (S) |  |  | 2020-01-22 | Jordan Conley | Assigned
Update L2 Makeup Slides and publish on Radius (S) |  |  | 2020-01-22 | Gwen Grant | Assigned
Draft Use Spec section of W-C-S012 (M) |  |  | 2020-01-22 | Jordan Conley | Assigned
Guidance Doc - Req&#039;t Map - Outline (S) |  |  | 2020-01-22 | Jordan Conley | Assigned
Guidance Doc ¦ Use Spec - Outline (S) |  |  | 2020-01-22 | Jordan Conley | Assigned
Roebling Update Communication (M) |  |  | 2020-01-22 | Gwen Grant | Assigned
Roll-out Communication Plan |  |  | 2020-01-22 | Gwen Grant | Assigned
Guidance Doc ¦ DEx - Finalize and Publish |  |  | 2020-01-22 | Gwen Grant | Assigned
Feedback L2T ¦ Overview of Procedure Impact |  |  | 2020-01-22 | Jordan Conley | Assigned
Feedback L2T ¦ Evidence Generation |  |  | 2020-01-22 | Gwen Grant | Assigned
Feedback L2T ¦ Interrelationship of Tools |  |  | 2020-01-22 | Gwen Grant | Assigned
Finalize the L3 Project List |  |  | 2020-01-22 | Gwen Grant | Assigned
Create Common Use Survey for L3 Partners |  |  | 2020-01-22 | Gwen Grant | Assigned
Guidance Doc ¦ Req Map - Draft |  |  | 2020-01-22 | Jordan Conley | Assigned
US Q4 Workshop ¦ RTM Transition |  |  | 2020-01-22 | Jordan Conley | Assigned
Guidance Doc ¦ DEx - Draft and Review |  |  | 2020-01-22 | Gwen Grant | Assigned
Automated data transfer of RTM into VRS |  |  | 2020-01-22 | Sol Posada | Assigned
Guidance on transforming CTGs into Design Inputs. |  |  | 2020-01-22 | Jordan Conley | Assigned
Agree on arrangement of W-C-S012: Appendix approach for Roebling process, or separate work instruction? |  |  | 2020-01-22 | Jordan Conley | Assigned
Resolve all open questions in the BDec Roebling Outline |  |  | 2020-01-22 | Jordan Conley | Assigned
Investigate country specific testing/staggered release; consider decoupling into different RTM sheets. |  |  | 2020-01-22 | Jordan Conley | Assigned
Claims associated with the new device are spread throughout the 4 categories: we need a way to track/highlight them in the matrix for evidence generation. |  |  | 2020-01-22 | Jordan Conley | Assigned
Writing procedure based FDRs will make it challenging to break out FDRs into several different ones for type of device like Delorean did (requirements are too intertwined). Will this be accepted? |  |  | 2020-01-22 | Jordan Conley | Assigned
Investigate: How does Evidence Generation (HEMA) feed into V&amp;V - Topic: Decomplexity. |  |  | 2020-01-22 | Jordan Conley | Assigned
Rationale for User Need / DI / DS: Guidance on how to write – what do well written examples look like? Including Business Needs. Maxframe question: What level of scrutiny will be expected from approvers (and eventual auditors) about the statements made in the Rationale field? Will there need to be evidence to support? |  |  | 2020-01-22 | Jordan Conley | Assigned
Do we need a standard way to address compatibility requirements between new device to new device + new device to existing device? |  |  | 2020-01-22 | Jordan Conley | Assigned
What is the required input to RC from VOC? What is required to be in the VOC summary? |  |  | 2020-01-22 | Jordan Conley | Assigned
Val / Ver Strategy: Guidance on how to write – what do well written examples look like? |  |  | 2020-01-22 | Jordan Conley | Assigned
&quot;Functional Analysis&quot; tool - is this in the RC workstream to produce, or is that PPS? Or has this evolved into the TFS now? |  |  | 2020-01-22 | Jordan Conley | Assigned
Draft Ankle Fusion with Use Spec and Req&#039;t Map (M) |  |  | 2020-01-22 | Jordan Conley | Assigned
Prep for Feb Town Hall (M) |  |  | 2020-01-22 | Gwen Grant | Assigned
Complete Reqt Map so TFS Confidence Eval can begin (M) |  |  | 2020-01-22 | Jordan Conley | Assigned
Weibull Stat Guidance |  |  | 2020-01-23 | Paul Scilingo | Assigned

## Votes
Identifier | Idea | Thumbnail | Total Votes | Average Vote | Brian Dec | Gwen Grant | Jan Valenzuela | John Tarczewski | Jordan Conley | Joy Iaconianni | Paul Scilingo | Sol Posada
d3c15d51-0b59-45da-a8c8-24f7f62b3242 | WI Update Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
aed04b18-f66f-4778-8299-3cb615aaef29 | Guidance Doc ¦ Req Map - Draft |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
502439fa-e4d1-4667-9027-1aa53050a2ff | US Q4 Workshop ¦ RTM Transition |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f2dac4ab-077d-41e0-8e89-c5c0d4afd3fc | Create Common Use Survey for L3 Partners |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11fc6fab-04a6-4edf-bf3a-5704a71f3890 | Guidance Doc ¦ DEx - Draft and Review |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a9a5a343-4ad0-4f53-8113-0d4cccb9abec | Implementation Execution ¦ L3 Training TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
946b1153-7991-4443-9aed-859f23dbd4c9 | Feedback L2T ¦ Interrelationship of Tools |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
677cea72-4316-4d77-bb4c-a8e15b7105c1 | Finalize the L3 Project List |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9fddb193-fb6a-417a-9528-e22d7541e11f | Implementation Execution ¦ L3 Training TFS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27eafe9a-0549-4e0f-846a-552c3410c957 | Create L3 Training Content |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a7f079ed-36b1-4550-9d16-f09ddc069da5 | Weibull Stat Guidance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86a032a7-5516-4bff-b15c-c50640d7c716 | L3 Training Dry Run w/ Ankle Fusion |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e14a2ff6-b28b-4c58-a6b0-59242f7a250e | CORe 3 of 6 ¦ Labeling (Gen1 Solution) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a5011a53-8ff1-468c-96dd-8ec053cd9bab | Guidance Doc ¦ Writing Good Requirements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7abc107d-9511-4d0d-a366-ce2088b14d29 | Feedback L2T ¦ Evidence Generation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
eaa8f6db-e75d-4a4f-9c44-fac97f1760ea | Feedback L2T ¦ Overview of Procedure Impact |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1fa9922c-0b34-4d81-8512-e7f7db462eb6 | Req. Spec. ¦ Procedure Based FDR vs. Device Specific |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79bc2bb2-942f-4bbd-a7fe-8a01516c3652 | CORe 3 of 6 ¦ Packaging (Gen1 Solution) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d884a657-00e3-4b7b-b59a-87ecbb74fec0 | DMD Assessment for L3 Training |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dbf38b19-18e4-4d06-9ff4-52c54e2e925a | Req. Spec. ¦ Part Number to Requirement Traceability |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9fdd6eea-ec6d-4f34-b251-e1d7b9aff46a | CORe 3 of 6 ¦ Bio Comp (Gen1 Solution) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2cf5501e-5d90-4e9d-82ed-71b13a04584e | Standard DEx Tool - Stakeholder Analysis - Phase 1 (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7d4bfe1f-087f-42d2-91cb-3be39f282698 | Standard DEx Tool - Multi-Generational Plan - Phase 1 (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b253a17d-8453-440b-ad09-922f069efe8c | RTM ¦ External Parts List |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2297942d-ad75-440d-975b-93d12d6c4a53 | CORe 3 of 6 ¦ F&DR S5 (Gen1 Solution) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97a5d209-6cdb-4c8d-83d6-26f4d38f52cf | Partner 7 of n ¦Maxframe Pilot |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254f673d-f68c-46da-89fe-9cfc9e3cfbbb | Roll-out Communication Plan |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4051f1f0-798e-4311-b0d5-8ebf89b7a9ec | Marketing Claims |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5fdbf7fd-0ab9-4e7e-9a84-858564bc7c8c | Guidance Doc ¦ DEx - Finalize and Publish |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
556c3852-9ba3-474b-b03b-4f40d1b8be94 | Guidance Doc ¦ RTM |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d99a3db6-f0a3-4846-a784-a61b7cfb2a4e | RTM ¦ Windchill Readiness |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a088c4c1-11be-4511-b67d-fc7197b0dafb | Complete Reqt Map so TFS Confidence Eval can begin (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7ced1f49-3cdb-4249-8b26-c054a61ff3e5 | Support Pelvis Formative Usability Labs (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1224992c-af16-4455-b77f-1006266120f8 | Prep for Feb Town Hall (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54534f13-fc63-4b8b-8309-2ade3e698444 | Req. Spec ¦ Draft "How to write V&V Strategy" (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ddfc35e8-05f7-4242-b5e4-7fa8ee7f137e | Coordinate w/ TPP workstream in Scope TTM (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
cad5771d-e7d8-4239-8b38-8b56f079c41b | Draft CA - Complete Remaining Redlines (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
696bb571-3022-400a-8ad0-22f8e554fb44 | Finalize & Post TFS Guidance (L) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b86d5231-1d10-43ae-b83f-e792d5580344 | Guidance Doc ¦ Dex - Develop Outline (L) |  | 3 | 0.375 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
40dedc17-5060-4686-a80d-ff8aef3e2778 | Convert Roebling (676) Process outline into 012 appendix 1 (L) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ca87be64-b39b-49cc-835c-39bb4982c607 | Review W-C-S012 - Resolve all open questions in the BDec W-C-S012 rewrite (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d6878255-7818-431a-9efc-e6828da0fd84 | Coordinate w/ Risk Management (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8deb8a51-275a-4cdd-afde-c81ce6477707 | Guidance Doc ¦ Use Spec - Outline (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d3ba1440-496b-4727-b01b-e0d7665a50a6 | Guidance Doc - Req't Map - Outline (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
842d1f1d-4f58-48db-884e-11639a7cfc77 | Guidance Doc - Procedure Map - Compare w/ W-C-S062 and outline (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a65c7e68-6886-4406-836f-d6b57efff791 | Learn Jonathan's RTM Validator Tool (L) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fcb62363-47a4-439e-b48d-96367eae82f4 | Update L2 Makeup Slides and publish on Radius (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
03af4e5b-d4e2-4bfc-8707-8f23e123211b | Make changes to documents in FROM folder (F&DR) (L) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3f594384-40fc-46dd-a19c-5d22dab251d9 | Draft Use Spec section of W-C-S012 (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
dcb08e04-3ed6-4f8a-81b0-67b85a985aa0 | Draft Roebling tab on Radius. Migrate info and retire Roebling external site (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1f60fb66-d055-43c3-b72e-08c035a26fda | Guidance Doc ¦ Outline VRS documentation for internal review (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f9c76287-8e46-4937-b3e5-9a0e31b65994 | Finalize "Essential Needs" Examples for PEC Review (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7b5d7992-7701-4ba8-8f02-ea9f4562cb33 | Finalize "Essential Needs" Definition (Phase 1) for PEC Review (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
feb3db3c-7f4b-425d-9a83-366ed40fd5a5 | Implementation Plan/ Milestone Chart (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b4a5df17-8264-49d0-9670-b1ab66466b96 | PLT Presentation (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
830e5ee7-b094-4694-a6cf-c4399fbc2489 | DMADVV Process Map (L) |  | 3 | 0.375 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
7c7d5a09-cc4e-4f79-a22d-e497ad53a53c | Support Pelvis team with Val labs (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0c5810cc-0024-41f6-8f5d-d4534f9c5350 | Identify Extended Review Team for Roebling Tools (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7b0d27e6-0b33-42d3-ba84-ae03fac281dc | Post Charter Process Map - VRS (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a9d02961-ef61-4c97-b2e8-56b1309612ee | Set up Future PEC Steering Committee Meetings (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
fe4bf3ef-f544-404c-9f3a-ae3b4575b70b | Roebling Stakeholder Exit Interviews (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b9b84d7e-4355-4e32-9646-26688eb17423 | Standard Tool Rollout Plan for 2020 (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b9ff6efb-d2bd-4deb-9457-3fa5f47821ca | Standard DEx Tool - SIPOC - Phase 1 (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
cb145e3a-4bfb-4cf6-a192-87a1259aa0c5 | Draft Ankle Fusion with Use Spec and Req't Map (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c7400d7e-a468-4149-af74-fe0d8f496768 | Post Charter Process Map - RTM (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
808fded8-f29e-4ddb-b52f-0f46522b2001 | Draft Agenda to cover with VA Clavicle team reconnect meeting (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
de93e0cd-defd-48e2-9243-81692bb3a9e1 | Mind Map Rollout Plan and align with team (S) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7a4bb8ba-4fd8-46e8-a1ab-38bfe3508030 | Kick off NPD R&D Playbook (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
933ab901-3faa-4b38-8956-90f04282ca13 | Finalize Use Spec Requirements (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390b4357-109c-47ab-bdbc-e837c7333777 | Guidance on transforming CTGs into Design Inputs. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8c8e2f12-74b8-4df7-8d5f-b0874811d621 | Investigate country specific testing/staggered release; consider decoupling into different RTM sheets. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71f08ea2-c9b2-4faa-8936-0caae28f50d6 | Writing procedure based FDRs will make it challenging to break out FDRs into several different ones for type of device like Delorean did (requirements are too intertwined). Will this be accepted? |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b9cdf08f-c285-410c-a41b-a9af209d0e73 | Rationale for User Need / DI / DS: Guidance on how to write – what do well written examples look like? Including Business Needs. Maxframe question: What level of scrutiny will be expected from approvers (and eventual auditors) about the statements made in the Rationale field? Will there need to be evidence to support? |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
cfbe8165-9cf2-47c1-86a2-94ad22b173af | Val / Ver Strategy: Guidance on how to write – what do well written examples look like? |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5d72d933-f1a4-4deb-a299-1289d45117ac | What is the required input to RC from VOC? What is required to be in the VOC summary? |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24d01553-47a6-40ab-bc56-6bf1eab61029 | "Functional Analysis" tool - is this in the RC workstream to produce, or is that PPS? Or has this evolved into the TFS now? |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88efb0f2-b905-4897-9ce6-9458e40043c9 | Do we need a standard way to address compatibility requirements between new device to new device + new device to existing device? |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9a2d3d0a-e390-4f48-af26-a046b03c900c | Agree on arrangement of W-C-S012: Appendix approach for Roebling process, or separate work instruction? |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7a3dc1d9-01d5-4822-8e28-ae122be16f20 | Resolve all open questions in the BDec Roebling Outline |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2bccd4d2-7f1c-4eac-858f-fa42820914b9 | Automated data transfer of RTM into VRS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19f773ef-00ca-4bb0-936a-ae26abbd7c04 | Claims associated with the new device are spread throughout the 4 categories: we need a way to track/highlight them in the matrix for evidence generation. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35301633-1709-42a0-8ff6-60c9b9c5c4bd | Investigate: How does Evidence Generation (HEMA) feed into V&V - Topic: Decomplexity. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6f0a6877-55df-4ee7-80ed-9a85e395e392 | Roebling Update Communication (M) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86e00723-ac2c-453a-b45b-8ac4dbaf85f3 | Conjoint Analysis Part 2 - release |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6dd5f8db-23ad-469f-847d-8cd17b8e591c | 1. Summarize task on regular sticky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5988432d-7300-4756-ba78-ce6dbe41ed06 | 2. Color code to legend and ALSO assign owner (click on bottom right of sticky) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c26a8c3f-3093-4610-bf5e-edf3c9bba410 | 3. Suggest using Comments to capture substeps or notes (OR can use Index Cards to capture substeps) Use @ to tag another team member |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
efc2012d-3235-4ac3-828d-eca60c61c8dd | 4. Arrange in Matrix of priority (low/high) and size (small, medium, large) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44230899-caeb-4522-bf9c-e265ccce1faa | 5. Use "Gem" shaped Stickies for new stories added during Sprint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ba2f8b29-d47c-45eb-8eaa-150499485fe1 | 6. Move stories from 'Done' to 'Archive' proceeding to next sprint |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
bc3639fb-62b7-480d-8107-01e5231bb74a | Link to Excel Tracking Report: https://jnj.sharepoint.com/:x:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B4AECE9EB-1B3F-41E1-85A3-495ABA4CED58%7D&file=Roebling%20Backlog%20and%20Sprint%20Plans.xlsx&action=default&mobileredirect=true |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
670bc3c5-0f2c-4bec-9ce9-60869e9ce2e6 | Link to Milestone Schedule: https://jnj.sharepoint.com/:p:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B10B1C622-4411-4698-95C7-7E91EF5E9AFB%7D&file=DRAFT%20Milestone%20Schedule%20-%20Q1%202020.pptx&action=edit&mobileredirect=true |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70facec2-0473-4611-ac7f-eab62241e753 | Link to RTM Questions: https://jnj.sharepoint.com/:x:/r/teams/Roebling2/_layouts/15/Doc.aspx?sourcedoc=%7B9AC12DF1-1D71-4DBB-9A8F-E770B9821D1E%7D&file=Req%20Cascade%20Questions%20to%20Answer.xlsx&action=default&mobileredirect=true |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0